## Exec_Summary
LATITUDE DIVESTMENT - TEST EXECUTION PLAN
Executive Summary
Tests
Total Number of Test Cases to be tested | 60
Test Status
Tests Executed | 1
Tests Passed | 0
Tests Failed | 0
Tests Blocked | 0
Tests De-scoped | 1
Tests In Progress | 0
Tests Deferred | 0
Tests Not Run (Awaiting execution) | 59
Defects
Total number of defects raised
Defects Open
Defects Closed
Defects awaiting Retest
RAG Status
Overall Status of Testing | Green
Caveats

## TFA_Status
LATITUDE DIVESTMENT - TEST EXECUTION PLAN
Test Summary
Test Focus Area | Pass | Fail | Blocked | Descoped | In-Progress | Deferred | Not Run | Total
Access Provided | 0 | 0 | 0 | 1 | 0 | 0 | 35 | 36
Access Restricted | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 17
User Experience | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7
Post-Divestment | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10
Totals | 0 | 0 | 0 | 1 | 0 | 0 | 59 | 60
| 0% | 0% | 0% | 1.667% | 0% | 0% | 98.33%

## Test Scenarios
LATITUDE DIVESTMENT - TEST EXECUTION PLAN
Test Scenarios & Requirement Traceability
Epic | Story | TS ID | Scenario Description | Test Focus Area
Link to Requirements Document

## Access Provided
LATITUDE DIVESTMENT - TEST EXECUTION PLAN | [8 empty] | Totals
Access Provided | [8 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 35
TS ID | TC ID | Test Case | Step | Expected Result | Actual Result | Status | Date Run | Comments | Pass | Fail | Blocked | Descoped | In-Progress | Deferred | Not Run
1 |  | Login
| 1.1 |  | Check the user is able to login on existing device | Username: tbc Password:tbc Scott to provide details |  | Not Run |  | logged in with dot.cotton. Is on corp.searchlatitude.com domain | 0 | 0 | 0 | 0 | 0 | 0 | 1 | intelligentmarketing
2 |  | Office 365 Tenant
| 2.1 |  | Check the Tenant ID for Latitute user is latitudedigitalmarketing.onmicrosoft.com | Scott to confirm |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 2.2 |  | Check the latitudegroup.com will be migrated from the existing TU UK tenant, callcreditgroup.onmicrosoft.com to the newly provisioned latitudedigitalmarketing.onmicrosoft.com tenant | Scott to confirm |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 2.3 |  | Check the domain is latitudegroup.co.uk for all divestment users | Scott to confirm |  | Not Run |  | logged in with dot.cotton. Is on corp.searchlatitude.com domain | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 2.4 |  | Check the domain is added to the latitudedigitalmarketing.onmicrosoft.com tenant | Scott to confirm |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
3 |  | Internect connectivity
| 3.1 |  | Check whether the laptop is connected to the support wired connectivity with local internet access providing for transport to the TU UK provided VPN Concentrators located in Warrington. | Allow accessing email account and browsing |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 3.2 |  | Check the Internet access provision is provided to connect to the TU UK VPN while roaming (connect from café ) Force Secure connect (Latitide own VPN) |  |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 3.3 |  | Check the Internet access provision is provided to connect to the TU UK VPN while working from home (connect to the mobile network) |  |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
4 |  | Exchange Online
| 4.1 | Naming Policy | Check Exchange Online breaks the naming policy for latitude users is set to LAT.GRP.EOL (Recommendation) | Recommendation by Exchange but not implemented to test |  | Descoped |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0
| 4.2 | Password protected file | Check Password protected file attachments will be scanned by Exchange Online Protection and delivered internally |  |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 4.3 | Shared Mailboxes | Check the following shared mailboxes are setup billing@latitudegroup.com, credit.control@latitudegroup.com, csteam@latitudegroup.com, developer.sent@latitudegroup.com, developer.testing@latitudegroup.com, purchaseledger@latitudegroup.com |  |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 4.4 | Service Mailboxes | Check all mailboxes are utilised to service applications and product within the Latitude infrastructure and these will need to be re-created in latitudedigitalmarketing.onmicrosoft.com | Scott to confirm |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 4.5 | DKIM – DOMAIN KEYS IDENTIFIED MAIL (Signature) | Check when email is sent from Lat->Lat, the signature is attached. DKIM signature signed with a private cryptographic key applied to the message headers of every email. |  |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 4.6 |  | Check when email is sent from Lat->Lat, the signature is attached as html appended file |  |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
5 |  | Skype for Business Online
| 5.1 |  | Check Skype for Business Online service has moved to the new O365 Latitude Tenant. | Scott to confirm |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 5.2 |  | Skype connection (Wired connection) & VPN |  |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 5.3 |  | Video & Audio call within latitude is allowed |  |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 5.4 |  | Check the configuration in the TU UK tenant is same as to the configuration in the latitudedigitalmarketing.onmicrosoft.com | Scott to confirm |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 5.5 |  | Check the latitudedigitalmarketing.onmicrosoft.com tenant has been configured to Allow specific domains(callcreditgroup.com, transunion.co.uk, transunion.com) |  |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 5.6 |  | Check Audio Conferencing is being leveraged by the Latitude business |  |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
6 |  | Security Controls
| 6.1 |  | Check latitude user can use the Latitude VPN solution which tunnels through the HSL data centre - 83.244.205.129/32 | Scott to confirm |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
7 |  | Azure Connection Group
| 7.1 |  | Check latitude users are in the 'AllUsers.GenericMailDisclaimer' group for automatic email signature | All users must be in this group for the email signature |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 7.2 |  | Check latitude users are in the Allusers.safeattachment group. Check for malware in the attachment sent by the user | All users must be in this group for sending attachments in email |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 7.3 |  | Check latitude users who has IOS device are in the Allusers.devicemanagement group. | Users who has IOS mobile device must be in this group |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
8 |  | Microsoft Teams
| 8.1 | Policy | Check number of policies are created within the Teams administration console that apply differing controls to the targeted users. • AllOff • AllOn • Global (Org-Wide default) • Kiosk • RestrictedAnonymousAccess • RestrictedAnonymousNoRecording | Scott to confirm |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 8.2 |  | Data(Text file) migrated from the current tenant to the new Tenant
9 |  | Microsoft OneDrive for Business
| 9.1 | One Drive | One drive folder is created in my document for the new tenant
| 9.2 | Default Storage | Check the allocate the maximum amount of storage space per OneDrive for Business account users in latitudedigitalmarketing.onmicrosoft.com tenant is 1024 GB. | Scott to confirm |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
10 |  | Intune & Device Management
| 10.1 | Policy | Check iOS compliance policy is assigned to Device Management – iOS Azure AD security group | Scott to confirm |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 10.2 | Outlook | Check iOS Email Profile is created to configure email for iOS devices. |  |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 10.3 | Profile | Check iOS Email Profile is assigned to the Device Management – iOS Azure AD security group | Scott to confirm |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 10.4 | Skype | Check Skype for Business is configured in iOS device |  |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 10.5 | Microsoft Teams | Check Microsoft Teams is configured in iOS device |  |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 10.6 | Attachment | Check sending the Macro files are qualified internally from a registered IOS device | email sent & recieved successful |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
11 |  | THREAT MANAGEMENT
| 11.1 |  | Check Symantec engine must rewrite the url sent via email (o365). Office 365 Advanced Threat Protection (ATP) is Microsoft’s offering for safe guarding corporate data against malicious threats borne via email messages, malicious URLs and collaboration tools | Scott to confirm |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 11.2 | Group Policies | Check Latitude Safe Attachments Policy is added to latitudedigitalmarketing.onmicrosoft.com and latitudegroup.co.uk | Scott to confirm |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 11.3 |  | Check Latitude Safe Links Policy is added to latitudedigitalmarketing.onmicrosoft.com | Scott to confirm |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 11.4 |  | Check Latitude Anti Phishing Policy – is added to latitudedigitalmarketing.onmicrosoft.com and extra phishing policy is applied to Senior Management Team i.e. 9 users | Scott to confirm |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1

## Access Restricted
LATITUDE DIVESTMENT - TEST EXECUTION PLAN | [8 empty] | Totals
Access Restricted | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 17
TS ID | TC ID | Test Case | Step | Expected Result | Actual Result | Status | Date Run | Comments | Pass | Fail | Blocked | Descoped | In-Progress | Deferred | Not Run
12 |  | O365
| 12.1 | O365 restricted outside the network | Check O365 should not be accessible outside the TU network |  |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
13 |  | Internect connectivity
| 13.1 |  | Check the internet connectivity when connected to Latitude_Guest | Access to o365 account blocked |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 13.2 |  | Connect to the Mobile hotspot and check for the Internet connection | Access to o365 account blocked |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
14 |  | Exchange Online
| 14.1 |  | Check Executable content file extension .exe, .dll, .vxd, .os2, .w16, .dos, .com, .pif are blocked to both internal and external users | Blocked |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 14.2 |  | Check Exchange Online Protection restrict Miscellaneous File Types.jar ,.obj & .rar (applicable - allowed access) files both internal and external |  |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 14.3 |  | Check Password protected file (zip) attachments will be scanned by Exchange Online Protection quarntine externally |  |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
15 |  | Skype for Business
| 15.1 |  | Check the latitudedigitalmarketing.onmicrosoft.com tenant has been configured to but block access to everyone else for external communication. |  |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
16 |  | IOS device (Registered User)
| 16.1 |  | Check sending the executable file(.exe file) internally from a registered IOS device | This must be blocked |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 16.2 |  | Check sending the executable file(.exe file) externally from a registered IOS device | This must be blocked |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 16.3 |  | Check sending the Password protected file(zip file) internally from a registered IOS device(Quarntine) | This must be blocked |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 16.4 |  | Check sending the Password protected file(zip file) external from a registered IOS device(Quarntine) | This must be blocked |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
17 |  | UK Financial Data
| 17.1 |  | Check sending financial data as a attachments(Word, excel, csv, xml, ppt, html, pdf), Subject line, message body in an email externally. Note: Financial data must contain (credit card details, EU debit card, Swift codes) | It should be blocked and get undelivery message to the sender |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 17.2 |  | Check sending financial data as a attachment in an email internal | Allow access |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
18 |  | UK Data Protection Act
| 18.1 |  | Check sending data file as a attachments(Word, excel, csv, xml, ppt, html, pdf), Subject line, message body in an email externally. Note: DPA data must contain (UK NI number, US / UK Passport number, Swift codes) | It should be blocked and get undelivery message to the sender |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 18.2 |  | Check sending data file as a attachment in an email internal | Allow access |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
19 |  | GDPR
| 19.1 |  | Check sending following details as a attachment (word, excel, pdf, ppt, csv, xml, html), subject line, message body. EU debitcard, Credit card, Driving licence number, NI, Passport, Social security no or equivalent id, Tax identification no externally | It should be blocked and get undelivery message to the sender |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 19.2 |  | Send the above file internal | It should be blocked and get undelivery message to the sender |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1

## User Experience
LATITUDE DIVESTMENT - TEST EXECUTION PLAN | [8 empty] | Totals
User Experience | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 7
TS ID | TC ID | Test Case | Step | Expected Result | Actual Result | Status | Date Run | Comments | Pass | Fail | Blocked | Descoped | In-Progress | Deferred | Not Run
20 | 20.1 | O365 | Office 365 portal https://login.microsoftonline.com/ | Reprofiled to new tenant |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
21 | 21.1 | Microsoft O365 email - Outlook | Microsoft Outlook 2016 | Reprofiled to new tenant |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
22 | 22.1 | Skype | Skype for Business | Reprofiled to new tenant |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
23 | 23.1 | Microsoft O365 Onedrive for Business | Onedrive | Reprofiled to new tenant |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
24 | 24.1 | Microsoft O365 teams | Microsoft teams | Reprofiled to new tenant |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
25 | 25.1 | Microsoft O365 OneNote | OneNote | Reprofiled to new tenant |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
26 | 26.1 | Internet connectivity | Wired, Guest user and hot spot | Wired - Allow access, Guest & hotspot - restrict access |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1

## Post-Divestment
LATITUDE DIVESTMENT - TEST EXECUTION PLAN | [8 empty] | Totals
Access Provided | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 10
TS ID | TC ID | Test Case | Step | Expected Result | Actual Result | Status | Date Run | Comments | Pass | Fail | Blocked | Descoped | In-Progress | Deferred | Not Run
27 |  | Post Divestment
| 27.1 | Exchange Distribution Group | Check all users are in lat.grp.mindcast.journalling group (Post Migration) | Applicable only post migration |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 27.2 | Inbound mail | Check native Exchange Online Protection engine is used. InboundConnector -Name : Latitude SMTP relay (Post Divestment) | Scott to confirm |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 27.3 | Outbound mail | Check the requirement for message journaling to occur between Office 365 and the historical 3rd party Latitude journal of Mimecast. OutboundConnector -Name 'Mimecast Journaling' (Post Divestment) | Scott to confirm |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 27.4 | Distribution Groups | Check the distributed groups are mirrored into the new latitudedigitalmarketing.onmicrosoft.com tenant with all membership and advanced configuration replicated. • latitudegroup.com • latitudewhite.com • latitude-express.com • cogneto.co.uk (Post Divestment) | Scott to confirm |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 27.5 | Application Impersonation - Cisco Unity Connection | Check all divestment users are added to Application Impersonation – Cisco Unity Connection LAT.SVC.CISCOUM group. Application impersonation to allow for Cisco Unity Connection to send emails on behalf of Latitude employee's when their associated profile receives a voicemail (Post-Divestment) | Scott to confirm |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 27.6 | Application Impersonation – Mimecast Sync Engine | Check all divestment users are added to Application Impersonation – Mimecast Sync Engine- LAT.SVC.MIMECASTSYNCENG group. Application impersonation for the Mimecast Synchronisation Engine running on LATIXMSE01 in HSL to be able to replicate the folder structure of Exchange mailboxes into the Mimecast Personal Archive. (Post-Divestment) |  |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 27.7 | Printers | Latitude printers are blocked from divestment users |  |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 27.8 | Remote Desktop Connection | Check login with the latitude user credential using Remote Desktop connection and it must be restricted (Post divestment) |  |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 27.9 | Hub | Hub is blocked for divestment users http://thehub.cig.local/Pages/Home.aspx | Access the hub home page is restricted |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 27.1 | Block TU US hub page | TU US hub as follows. Name: thehub.transunion.com URL: https://thehub.transunion.com Address: 10.216.36.58 The above resides in the proxy exceptions and should be blocked by default. |  |  | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1

## Lookup
Pass | ✓ | Red
Fail | ✕ | Amber
Blocked | NA | Green
Descoped | Not Checked Yet
In-Progress | Not Fully Complete
Deferred
Not Run