## Exec_Summary
Rollback testing - TEST EXECUTION PLAN
Executive Summary
Tests
Total Number of Test Cases to be tested | 8
Test Status
Tests Executed | 7
Tests Passed | 7
Tests Failed | 0
Tests Blocked | 0
Tests De-scoped | 0
Tests In Progress | 0
Tests Deferred | 0
Tests Not Run (Awaiting execution) | 1
Defects
Total number of defects raised
Defects Open
Defects Closed
Defects awaiting Retest
RAG Status
Overall Status of Testing | Green
Caveats

## TFA_Status
Rollback testing - TEST EXECUTION PLAN
Test Summary
Test Focus Area | Pass | Fail | Blocked | Descoped | In-Progress | Deferred | Not Run | Total
Rollback testing | 7 | 0 | 0 | 0 | 0 | 0 | 1 | 8
Totals | 7 | 0 | 0 | 0 | 0 | 0 | 1 | 8
| 87.5% | 0% | 0% | 0% | 0% | 0% | 12.5%

## Test Scenarios
Rollback testing - TEST EXECUTION PLAN
Test Scenarios & Requirement Traceability
Epic | Story | TS ID | Scenario Description | Test Focus Area
1 | 1 | 1 | RollBack testing
Link to Requirements Document
https://callcreditgroup.sharepoint.com/:x:/g/coo/etd/ITResilienceProgramme/EUEZKXNto3hCnQT6-lqkXsYBmttx9kUrZhBe8g7KXEi_jQ?e=miNcf7

## RollBack
Rollback testing - TEST EXECUTION PLAN | [8 empty] | Totals
Rollback testing | [8 empty] | 7 | 0 | 0 | 0 | 0 | 0 | 1
TS ID | TC ID | Test Case | Step | Expected Result | Actual Result | Status | Date Run | Comments | Pass | Fail | Blocked | Descoped | In-Progress | Deferred | Not Run
1 | 1.1 | Clear out Optimus Disputes in System Test | Check the system test database is cleared | System test db must be cleared | System Test environment cleared of all disputes in both Numero & Supplier Portal | Pass | 2019-10-23 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | Populate Optimus with Disputes for Validation | Check disputes have been created | Disputes created at varying status. Some in Ginger awaiting submission, some already in Numero and some already in the Dispute Portal | Disputes successfully created | Pass | 2019-10-28 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | Disputes 'Auto-Closed' | Check all the In-Flight disputes were auto-closed | All In-flights were auto closed | Evidence shows before and after status changes from 'Awaitng Investigation' to 'AUTO COMPLETED (REGRESSION)' Also screens of Numero Interacive showing cleared down | Pass | 2019-10-28 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | In-Flights read in NI | Check In flight disputes which have been read into numero Interactive via the scheduler and are awaiting manual actioning will be moved to a closing outcome. | All In-flights in NI were closed | Evidence shows before and after status changes from 'Awaitng Submission' to 'AUTO COMPLETED (REGRESSION)' Also screens of Numero Interacive showing cleared down | Pass | 2019-10-28 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5 | Supplier reponses & requests | Check all in-flight Supplier Responses and Requests were auto closed | All in-flight Supplier Responses and Requests were auto closed | Evidence shows before and after status changes from 'Awaiting Supplier' to 'AUTO COMPLETED (REGRESSION)' Also screens of Numero Interacive showing cleared down | Pass | 2019-10-28 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | MI against disputes cleared | Validate MI against disputes cleared | Report which shows everything that has been auto-processed by the regression scripts. Disputes, SLA Notifications, Supplier requests etc. This report is just a flat SQL output of everything affected | Query about SLA counts not correlating | Not Run |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 1.7 | Numero to accept disputes post rollback | Check and confirm that disputes flow correctly to Optimus post-rollback script execution | Disputes are accepted by optimus with correct id allocation and statuses | Evidence showing Ginger disputes accepted and prcessed successfully. Dispute present in Nuemro Interactive and in Supplier Portal | Pass | 2019-10-28 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 1.8 | Numero to Send status updates back to Ginger and Ginger to accept | Check and confirm that as disputes are processed by Numero post rollback, status updates are sent to Gimger and accetped | Status updates sent to Ginger and visible in portal | Evidence showing dispute at Complete Successful in Ginger | Pass | 2019-10-28 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0

## Lookup
Pass | ✓ | Red
Fail | ✕ | Amber
Blocked | NA | Green
Descoped | Not Checked Yet
In-Progress | Not Fully Complete
Deferred
Not Run