## Sheet2
Environment | COO Test Functions | Confidence level | Environment limitations (stubbing) | Risks accepted | Assumptions
System Integration test | NODS & Suppressions | 85% | No stubbing was in place, rather the testing was limited to proving that the NOD's and Suppressions sprocs had been called and the staging and audit tables had been populated. Testing that the staged records processed was not possible as JCS jobs are not running in the environment. Additionally it should be stressed that the scope of Optimus testing was always only to test that sprocs were called and data staged as the testing of the processing of these records was performed and signed off by the product team prior to Optimus project SIT test phase. | 1. We have proven and evidenced each dispute type was tested in System Integration Testing in Sept/Oct last year, but this was only as far as the staging tables. Due to environment restrictions it was not possible to test beyond this point. 2. Test Consumers were created via DBfit to have existing test consumer IDs in the call report. 3. Ginger & Noddle test credentials were supplied for testing by respective product team | Staging tables setup as required.
| IDAM | 71% |  | 1. All tests executed have proven the IDAM functinailty is functioning as expected including full end to end testing of the complete system 2. It is recommended the open defects listed above although low priority are fixed before Day 1 Go-Live as these could generate additional calls to the Client Service Desk | 1. Due to the System Test and Integration Test environments being in the same Azure Tenant it was possible for accounts generated in System Test to access the IDAM system in Integration Test . This should not be an issue with QA/PreProd or Prod as these will have seperate Azure ADB2C tenants. These should be tested as a part of negative testing in the PreProd environment.
| UAT - Functionality | 85.3% | Data approach was to use DBFit scripts to create test data in Bureau and Call Report databases. | Defects converted to Change Requests to be completed post Go-Live. 12, 17, 20 , 21 , 24 , 25 , 26, 44, 47, 51, 54, 74 | Confidence level is based on the testing done by respective test team.
System Test | Change Request by raised from SIT (IDAM) | 100% |  | • Confirm self-service password links are removed or user is redirected to a custom page (1 test) - Microsoft have confirmed this is not feasible. Project group have accepted this risk by including additional guidance in the user guides and registration emails
| Business Processes (Supplier Maintence config portal & IDAM) | 96.15% |  | • Changes to the Supplier name in the config portal not reflecting in IDAM for existing assigned users (2 tests) - This activity is not a common event and will not affect access to disputes. Project group agreed this will be considered in future releases of the system
| CR045 & CR046 | in progress | No existing data to test the specific scenarios was available so DBFit scripts were created to insert the data into Bureau and Call Report databases.
| Data proving from Ginger & CK & Roll back (Not yet started) | 0%
UAT team
CR045 & CR046
| Change Request raised by CDP team | 89% |  | • CR030 - Drivve Printer Software Metadata - Document Scanning (1 test) - This is required for Contact Management and not Dispute Processing • Consumer search on previous addresses (1 test) - This is not possible now in Bizagi and the CDP team use Callreport. CDP team have agreed to follow existing processes using Callreport
Preproduction | NODS & Suppressions | 87% | Regression testing of NOD's and Suppression was performed and as the preproduction environment has necessary JC jobs running it was decided to progress the staged records and verify that the NOD's and Suppressions are applied accordingly. This was beyond the initial scope of Optimus testing but was decided that it would be a good confidence building exercicse. Note that help was required from Product Team due to some evironmental restrictions where jobs do not run exactly as per production, such as non-weekend running. | Staging of add and remove NOD's is proven for all dispute types. Staging of add and remove suppression for the 3 in scope dispute types MODA, Associate and Share is proven. Note: Testing has exposed that some functionality has not been implemented on the back end, specifically the NOD's for MODA and Insolvency and suppressions for associate disputes.
| OAT testing | 100%
| Noddle connectivity | 0% | Ginger and Noddle/CreditKarma preprod point to different version of call report to Numero | Unable to test end to end as preprod ginger and noddle point to different versions of call report, but we could prove that numero rejected disputes sent through due to data mismatch, and also that noddle rejected status updates as id's were unrecognised for example. So proved connectivity. | We have proved it in system test environment.
| Ginger Connectivity | 0% | Ginger and Noddle/CreditKarma preprod point to different version of call report to Numero | Same as above | We have proved it in system test environment.
| CallReport Interface | 100% |  | Testing will use Test consumer IDs already existing in Preprod Callreport & Bureau. eg. John Ferrari for logging manual disputes via NI
| Bureau Integration | 100%
| IDAM | 100%
| Numero Interactive | 100%
| Supplier Configuration | 100% |  | Supplier config will be updated manually to match John Ferrari Supplier details. ie Create Supplier, Portfolio ID & Portfolio Name
Production |  |  |  | I would like to raise a risk in regards to Production environment testing. This is in relation to the testing of the addition and removal of NODs and Suppressions. Our intention all along was to use existing test data that we believed existed across ST, Preprod and Production environments. It has been confirmed today by the DBA that this data set only exists in Callreport and there are no matching entries in Bureau which means we are not able to run NOD & Suppression tests with test data in the Production environment. Due to security constraints it is not feasible to create new test data in the Production Bureau and CallReport environments. Risk Mitigation We have proven and evidenced each dispute type was tested in System Integration Testing in Sept/Oct last year but this was only as far as the staging tables. Due to environment restrictions it was not possible to test beyond this point. We are currently in the process of proving NOD and Suppression testing in Preprod. It needs to be proved in Preprod that we can process NODS to the staging tables and into the master tables for all dispute types. This will minimize the risk in Production as the Preprod environment should be configured the same. | Issues - It is not be possible to process a dispute from Noddle & Ginger until live cut-over as they are both live interfaces currently pointing at Bizagi (Starting point for smoke testing will be NumeroInteractive)
| NODS | 100% |  | Add NODS has been checked for Amex share dispute types only | We have proven and evidenced each dispute type was tested in System Integration Testing in Sept/Oct last year but this was only as far as the staging tables. Due to environment restrictions it was not possible to test beyond this point. We are currently in the process of proving NOD and Suppression testing in Preprod. It needs to be proved in Preprod that we can process NODS to the staging tables and into the master tables for all dispute types. This will minimize the risk in Production as the Preprod environment should be configured the same.
| OAT | 0%