## Sheet1
Defect No | Priority | Description | Test data requirement | Test performed by
282 | Critical | **numero-CR059** Add Credit Karma (CK) as a 'Ginger' supplier Source. | No particular requirement for manual – will re-use any other consumer. Will need an API consumer with a CK account. | Raminta / Hema
253 | High | **numero** *CR051* Unable to move portfolios from one supplier to another supplier - will impact the ability for the client to process disputes go-live | No data requirement | Hema
258 | High | **numero** Automatically rejected disputes left open | Will recycle any existing consumer – no particular requirement | Raminta
275 | High | **numero - CR057** Supplier response can contradict success outcome for Search, Alias and Address Link. | Manual and API consumer with a search, 2 Alias links, and an Address Link | Raminta | Search pending | HARRY JERRY | 8 CLARE COURT PRESCOTT STREET HALIFAX HX1 2QA | 1990-07-15
276 | High | **numero** Alias link disputes not reaching the supplier portal | Will reuse the ones for 275, no separate requirement | Raminta
279 | High | **numero-CR058** disputes where there is a file merge are auto routed to supplier - REQUIRED FOR GO-LIVE | Manual and API consumer with a file merge; I’ll add the requirements in a separate table below | Raminta | Moda and Search pending | MARY JERRY | 8 CLARE COURT PRESCOTT STREET HALIFAX HX1 2QA | 1987-07-15
284 | High | Multiple work items created for a single dispute | No data requirement – was a one-off issue, also spotted while testing CR046 – I’d suggest to descope as we were unable to recreate the same issue since it happened. | Raminta
288 | High | * TU Triage * Disputes unactionable after receiving evidence | A consumer with ER, Bankruptcy, and CCJ (both manual and API) | Raminta | done | NEMO FISH | 8 CLARE COURT PRESCOTT STREET HALIFAX HX1 2QA | 1991-07-15
290 | High | Noddle branding present in email receipt confirmation | Will recycle any existing consumer – no particular requirement | Raminta / Hema
- REQUIRED FOR GO-LIVE
299 | High | CR062 - Testing of backout of CR046 | Detailed in a separate table below | Raminta
279 File Merge setup for manual and Ginger consumers: (2 consumers in total)
Person 1 (disputer): | Person 2:
|  | MARY JERRY | MARY BERRY
3 addresses | 4 addresses | 1987-07-15 | 1987-08-15
2 Shares | 2 shares | Current address: | Current address:
1 Associate Link | 2 searches | CLARE COURT, 8 PRESCOTT STREET, HALIFAX, WEST YORKSHIRE HX1 2QA | CLARE COURT, 11 PRESCOTT STREET, HALIFAX, WEST YORKSHIRE HX1 2QA
2 searches | 1 IVA | One SHARE registered under this address | The two SHARES are registered under this address
ER data | ER data | Both searches are also under this address | One search under this address -
|  | ER at this address | ER at this address
Current address: | Current address: |  | MODA
CLARE COURT, 8 PRESCOTT STREET, HALIFAX, WEST YORKSHIRE HX1 2QA | CLARE COURT, 11 PRESCOTT STREET, HALIFAX, WEST YORKSHIRE HX1 2QA | Previous addresses:
One SHARE registered under this address | The two SHARES are registered under this address | CLARE COURT, 9 PRESCOTT STREET, HALIFAX, WEST YORKSHIRE HX1 2QA | Previous addresses
Both searches are also under this address | One search under this address - | Empty | CLARE COURT, 12 PRESCOTT STREET, HALIFAX, WEST YORKSHIRE HX1 2QA
ER at this address | ER at this address |  | IVA is under this address
| MODA | CLARE COURT, 10 PRESCOTT STREET, HALIFAX, WEST YORKSHIRE HX1 2QA | One search under this address
Previous addresses: |  | One SHARE at this address | ER at this address
CLARE COURT, 9 PRESCOTT STREET, HALIFAX, WEST YORKSHIRE HX1 2QA | Previous addresses | ER at this address
Empty | CLARE COURT, 12 PRESCOTT STREET, HALIFAX, WEST YORKSHIRE HX1 2QA | MODA | CLARE COURT, 13 PRESCOTT STREET, HALIFAX, WEST YORKSHIRE HX1 2QA
| IVA is under this address |  | Empty
CLARE COURT, 10 PRESCOTT STREET, HALIFAX, WEST YORKSHIRE HX1 2QA | One search under this address | The associate link exists at all three addresses
One SHARE at this address | ER at this address |  | CLARE COURT, 10 PRESCOTT STREET, HALIFAX, WEST YORKSHIRE HX1 2QA
ER at this address |  |  | ER at this address
MODA | CLARE COURT, 13 PRESCOTT STREET, HALIFAX, WEST YORKSHIRE HX1 2QA
Empty
The associate link exists at all three addresses
CLARE COURT, 10 PRESCOTT STREET, HALIFAX, WEST YORKSHIRE HX1 2QA
ER at this address
299 – backing out of CR046, both manual and API (12 consumers in total)
1 | Consumer with at least 3 addresses and a Share | MARY JERRY | 8 CLARE COURT PRESCOTT STREET HALIFAX HX1 2QA | 1987-07-15
2 | Consumer with at least 3 addresses and a MODA | PENDING
3 | Consumer with at least 3 addresses and a BAI/IVA | TOM JERRY | 8 CLARE COURT PRESCOTT STREET HALIFAX HX1 2QA | 1977-08-15
4 | Consumer with 4 addresses, SHARE registered at the end of chain address | SAM WATSON | 8 CLARE COURT PRESCOTT STREET HALIFAX HX1 2QA | 1967-07-15 | Share attached at 11 clare court
5 | Consumer with 4 addresses, SHARE registered at a middle of chain address | SHERLOCK HOLMES | 8 CLARE COURT PRESCOTT STREET HALIFAX HX1 2QA | 1983-07-15 | Share attached at 10 clare court
6 | Consumer with 4 addresses, end of chain address link has no data | JOHN TATE | 8 CLARE COURT PRESCOTT STREET HALIFAX HX1 2QA | 1984-07-15